## User stories
Sprint | Story Number | Story | State
1 | 1 | As a user I would like to interact with an interface that provides basic spellchecking | Completed
2 | 2 | As a user, I would like to receive spell checking without having to click a submit button | Completed
2 | 3 | As a system admin, I would like to develop the back end in Python and link it with JavaScript | In Progress
3 | 4 | As a user, I want to be able to replace a word by right-clicking on the word and a menu showing different choices. | In Progress
3 | 5 | As a user, I want to have an ideal user experience by using a well designed application. | Completed
4 | 6 | As a user, I would like to received context spell checking, not only by dictionary | In Progress

## Bug Log
Bug Number | Reported by | Description | Priority | Status | Sprint | Assigned to | Notes
1 | Julian Ramirez | Node is triggering an error when the array that contains the words is empty. | Low | Pull Request Created | 3 | Julian Ramirez
2 | Julian Ramirez | When user is typing in the div, sometimes it adds a space after the last word. | Medium | Assigned to a Sprint | 4
Priorities
[8 empty] | Low | There is little to none impact in user experience and functionality
[8 empty] | Medium | There is some impact in the user experience but not application functionality
[8 empty] | High | There is a considerate impact in user experience and/or functionality
[8 empty] | Critical | Functionality is in jeopardy, user may not be able to get accurate spell checking
Status
Assigned to a Sprint
In Progress
Development Completed
Pull Request Created
Fixed
Created by
Kimaya Gandhi
Manasa Gade
Sai Priyatham
Julian Ramirez